## Sheet1
TO-DO LIST |  | coding effort estimation (average) | SITE LISTS | COMETS REQUESTS |  | PRIORITY LIST - NEW
priority:
--!!! fix breaking order (you should always break from the side your goal is on |  |  |  | add Starcade Wiki link to fooer |  | PLAYER EXPERIENCE
--mobile playability |  | 4 | strawgames | update e-mail to contact@starcade.io |  | -- In-game instructional text tips | * note: when referring to "YOUR BALL" it should be colored in YOUR color
--inventory | slots | 1 | y8.com | add in-game tip text |  | -- Add in-game visual indicators- puck pointer, 'floatting' goal pointer, goal glow when scores
--chat [fade text out, close it, click player name -> mute/report] | paging | 1 | https://gamewith.jp/ | change leaderboard "Playtime" text to show HOURS not days |  | -- Adjust break pattern so it offers better spread and doesnt result in scoring your own ball - try rotating the circle a few degrees and geting staff to try it out
goal glow | scroll | ?? | armorgames | add equipable GM / Tester / SF rank icons | x | -- Add goal placement restrictions - so they can only place puck inside the 2 circles on your territory
| tooltip | 3 | 4j | update the rank icon names based on the updated image | x | -- Add automated goalie that moves up and down slowly in front of goal - only interacts with Puck
| or separate preview | 1 | gleamplay | align the table better on mobile (centered but room for power bar - top HUD seems small too |  | -- Fix start-round ball breaking so the player always breaks on THEIR side of the table
| sorting | 1 | kizi | add pop-up for exitting tthe game prematurely "Exit Game? Yes - No" |  | -- Add pocket blocket 'power-up' mechanic
| promote code | 2 |  |  |  | -- Fade chat message after 8 seconds
| database | 1 |  |  |  | -- Add ability to click players names to mute them (later we can have a dropdown)
| coin | 1 |  |  |  | -- Fix curse filter so all the words arent blocked - via a 'whitelist', by hand, or by some app
[5 empty] | x | ** Optional, we can make a 'menu' icon on top right to bring up settings window for chat, audio, etc
-- adblock "an ad appeared and disappeared with adblock detection saying 'ad blocked'" |  | ?
--mobile screens |  | 10
--warm up mode (allows players to shoot balls around while in queue, very nice feature while we build player base and low pop) |  | 5
-- add xmas promo assets to game and give it to everyone who has or will sign up until January 5th(edited) |  | 1
non-priority:
--add new avatars as rank rewards |  | 1
-- change ball shadow's z-index so its render BELOW balls, puck, goals, and table border |  | 1
-- rank icons still small in results screen |  | 0.5
--score missing from results screen |  | 0.5 |  |  |  | GAMEPLAY
-- Facebook/twitter promo on menu
--footer area on results screen doesnt line up with the rest of the UI/missing center banner (we'll look into this screen more later) |  | 0.5 |  |  |  | -- Add 15% power to overall shot power - we want balls to travel and split up better - especially on break - players wants balls to move more like 8-ball physics
--proper 'round complete' animation or atleast the text graphic |  | 0.5 |  |  |  | -- Increase ball attenuation - so it rolls further - it currently stops abruptly or only rolls a short period of time
-- Add 5 seconds to shotclock overall (to help for mobile players)
-- figure out a way to deal with AFK players (shorten shot clock time to 5 seconds if they havent done anything for X minutes) |  | ? |  |  |  | -- If you have ball-in-hand, add 10 extra seconds to shotclock
-- show tooltip when hovering over rank icon (shows rank name and number) |  | 3 |  |  |  | -- Puck attenuation is too long - it should come to a stop 20% faster
- If delta time is too large on the server, it's possible collision will skip too far. We had a case where it skipped right over a ball |  | 5 |  |  |  | -- Finish Inventory
Do physics and cue stick rotation client side, the same way you do it serverside. Because during lag, the cue stick is obnoxious and ball physics aren't smooth. Just verify the input on the server before initiating the move on the client side. It's deterministic if you do that right As an aside, what if the puck hardly moved the other balls when it hit against them? Like pretend like the puck is really light. Would that be a better interaction? |  | 5 |  |  |  | -- Release update - inventory, new player instructions, promo codes, facebook/twitter promo, new table/goalie/pocket mechanic
Add 18pt troika text bottom right of table "Player x's turn", "Player x scratched", etc |  | 1
Add 'bad' sound for shooting wrong ball/puck in |  | 0.5 |  |  |  | * Add ball in hand restrictions - so they can only place ball in your territory
managemennt:
-- command for retrieving player ID |  | 0.5
-- add GM room or console we can execute commands without joining a game |  | 0.5
-- add !kick !ban !squelch <player ID> |  | 0.5
-- \scorereset <player> resets score, if left empty, resets own score(edited) |  | 0.5
 Searching for opponent is off-centered |  | 0.5
 Force landscape mode at all times |  | ?
Mobile
 Aiming – the ‘point to ball’ aim mechanism is not ideal for this type of game. We need something more like 8-ball where you can rotate the stick by dragging it from the frontside and backside. The rotation should also be much slower than the player’s touch, this will help the player get precision aiming |  | 1
 Ball/puck Penalty – we need to emphasize the the ability to drop the ball/puck, I will make a background icon for this, but we should also include some text-based instructions as well. |  | 1
We need text-based instructions for a lot of things for both mobile and desktop (Player's turn, Player fouled!, Player scored puck!, etc) |  | 1
 Set breakpoint values for background illustrations hide at 1200px / set background image to scale to fit display (?)(edited) |  | 0.5
Marketing
-- upload game to itch.io - https://itch.io/docs/creators/html5 |  | 1
- miniclip, y8, armor games
-- 4j, gamegame.com.ua, armor-games
-- submit game to agar.io developer - he promotes it on social media https://github.com/Matheus28/studio
-- release beta gameplay trailer with mobile (app?) launch
-- create streamer promo pack (stick, twitch/youtube table decal + custom avatar of their choice?)
-- create 'Like Us' promo pack (stick (youtube), avatar (facebook), table decal (twitter) for players who share/like us on social media
reddit
Hey what the fuck you doin down here mate?